## Guidance
GLOBAL POVERTY ACTION FUND (GPAF) LOGICAL FRAMEWORK TEMPLATE WITH ACTIVITY LOG A logical framework or logframe is required for all GPAF projects. IMPACT WINDOW Applicants must complete the first two columns and activities log of the logframe template and submit together with their concept note. Applicants invited to proposal stage will be asked to fully complete all sections of the template. For guidance on logical frameworks please refer to the How To Note. Further guidance is available in the Impact Grant Guidance notes. IMPORTANT INFORMATION ON COMPLETING THE LOGFRAME • Each logframe must be saved as a separate file in Excel format (*.xls) • The logframe must not include any more than 6 (six) outputs • The logframe must not exceed a total of 155 spreadsheet lines • The font should be no smaller than Arial 9 when completed Logframes which do not conform to the above criteria will not be considered.

## Logical Framework
PROJECT NAME | Achieving development effectiveness through improved UK NGO (non-governmental organisation) practice and transparency, and collective influencing of European Union (EU) and international development goals
SUPER - IMPACT | Super - Impact Indicator |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016) | These super-impact level milestones are an important part of Bond's theory of change, but Bond is not responsible for the delivery of these goals and this will not form part of regular reporting.
More effective development co-operation is increasing long-term impact for people living in poverty | Progress towards achieving the Millennium Development Goals (MDGs) accelerates in the run-up to the 2015 deadline and initial progress is made against internationally-agreed post-2015 development targets | Planned | Some MDGs are on track to be achieved, others are lagging behind. Initial negotiations have commenced on the post-2015 framework (including the publication of the High Level Panel (HLP) report) | Negotiations to agree a post-2015 framework are making progress, including outreach and consultation with civil society, and progress toward the achievement of all MDGs has accelerated from current trends. | Negotiations to agree a post-2015 framework conclude with endorsement from civil society. The MDGs are achieved. | Implementation of the new post-2015 framework commences, with the support of civil society. | A new, ambitious post-2015 framework is agreed and endorsed by civil society. The MDGs are achieved.
Achieved
Source
Official UN MDG reports
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016) | We understand "making more informed decisions and positive changes" to mean that people within NGOs acquire the skills, confidence and knowledge to recommend changes; achieve the buy-in and support of their organisation to enact it; and implement a change to organisational or programme practice that results in, or is expected to result in, an improvement to development outcomes. At the impact indicator level, we are assuming that the 'target audience' is all Bond members, plus all Network of International Development Organisations in Scotland (NIDOS) and Coalition of Aid & Development Agencies (CADA) members (pending detailed discussions with CADA), plus all Department for International Development (DFID) grant holders. This indicator requires significant changes in organisational approaches. Based on our past experience working with this target audience, achieving 10% reported changes is an achievable but ambitious target. EU Member States "feeling pressure" means that they are aware of support for 0.7% and the Multiannual Financial Framework (MFF) from the public, media and EU NGOs. Annual NGO reports will be produced by Bond and partner networks and organisations to monitor the progress made by EU Member States on these issues. These will be used as lobbying tools to further exert pressure on EU Member States. The exact influencing activities used will be determined by a power analysis, but are likely to include lobby meetings, briefing papers, events, media work and the dissemination of research and analysis. A power analysis will be conducted for each year of the grant, by the end of the first quarter. The focus for our 2016 target here relates to big Member States which are currently off track on their aid commitments (France, Germany, Italy, Spain) as this would have the greatest impact on the overall aid budget.
The programme's target audience* play a key role in achieving development commitments through meeting their own effectiveness goals, and influencing European Union (EU) and international development policy and practice | % of our target audience* report making more informed decisions (through using International Aid Transparency Initiative (IATI), Bond effectiveness tools) focused on increasing effectiveness | Planned | N/A | Baseline survey of target audience reporting making more informed decisions and positive changes. | 5% increase in target audience reporting making more informed decisions and positive changes (from baseline) | 10% increase in target audience reporting making more informed decisions and positive changes (from baseline) | 10% increase in target audience reporting making more informed decisions and positive changes (from baseline)
Achieved
Source
Annual survey; In-depth interviews with a sample of users of the NGO Information Platform and evaluations of the users of other effectiveness services
| Impact Indicator 2 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| EU Member States feel pressure to reach their targets on aid quality and quantity (0.7% and Multiannual Financial Framework (MFF)), and European development policy and practice has a clear focus on poverty-reduction | Planned | Majority of EU Member States off-track on aid effectiveness and aid quantity (0.7%) commitments. NB: Bond to review annual milestones with DFID at the beginning of each year to identify any more specific indicators to evidence progress towards the target, given the specific EU policy landscape prevailing at that point. | The new MFF maintains European Aid levels | The majority of EU Member States make accelerated progress on their aid targets and aid effectiveness (in line with the goal of all EU Member States reaching 0.7%) | At least one big EU Member State delivers aid targets and aid effectiveness commitments | Evidence of progress by European Commission to deliver their aid effectiveness commitments (in implementation plans), aid remains on the EU's political agenda each year and evidence that EU development policy remains focused on poverty reduction. (April 2016)
Achieved
Source
EU Member States' commitments, AidWatch and; Annual NGO reports and influencing activities that track the EU and Member States' delivery of their aid quantity and quality commitments. (See point under baseline on specific indicators.)
| Impact Indicator 3 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016) | An "ambitious" post-2015 development framework would include clear and achievable goals that will guide national and international actors in their work to reduce global poverty. It will capture a range of issues identified as important in the new global landscape of poverty, including inequality and crucially it will tackle the root causes of poverty. 2 examples of engagement each year will maintain momentum over this period, with chosen representatives communicating the views of the civil society alliance. In addition, while there may be ongoing informal discussion and dialogue with policy makers, we consider 2 examples of engagement as our minimum standard.
| The ‘Beyond 2015’ civil society alliance mobilises support to ensure the international community agrees and commences implementation of an ambitious global post-2015 development framework | Planned | Some limited dialogue takes place between Bond's target audience and policy makers | At least 2 clear examples of meaningful engagement between Bond's target audience and policy makers following on from the Sept 2013 post-MDG review (for example NGOs consulted on post-2015, meetings between NGOs and policy makers) | At least 2 clear examples in this year of meaningful engagement between Bond's target audience and policy makers in response to relevant policy processes around the post-2015 process (for example NGOs consulted on post-2015, meetings between NGOs and policy makers) Final plans made on the post-2015 framework reflect the civil society alliance position | At least 2 clear examples in this year of meaningful engagement between Bond's target audience and policy makers in response to relevant policy processes around the post-2015 process (for example NGOs consulted on post-2015, meetings between NGOs and policy makers) The first year of implementation of the post-2015 framework corresponds with plans that reflect the civil society alliance position | A legitimate consultation process (of at least 6 cumulative meaningful examples of engagement) between Bond's target audience and policy makers has informed the development of an ambitious global post-2015 development framework. The first year of implementation of the post-2015 framework corresponds with plans that reflect the civil society alliance position
Achieved
Source
Meeting and communication records kept by Bond; Comparison/analysis of our goals with key policy statements including different United Nations (UN) reports such as from the High Level Panel, the UN Secretary General to the General Assembly of the United Nations (UNGA), the Open Working Group on Sustainable Development, as well as outcome documents from relevant UN General Assembly meetings.
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016) | Assumptions
The programme's target audience* effectively and efficiently achieve their own organisational goals and exhibit best practice | # of individuals citing evidence of positive changes in their practice as a result of applying knowledge/ skills gained from (a) training and (b) networking facilitated by Bond [subset of those in Output 1.1.2] | Planned | N/A | 500 (50% of 1,000 trainees) | 605 (55% of 1100 trainees; annual target) | 726 (60% of 1,210 trainees; annual target) | 1,831 (60% of 3,310 trainees by grant end) | Bond can develop a robust method for eliciting evidence of improvements in effectiveness that can be credibly linked to support received from Bond. This will include triangulating a sample of individual survey responses by conducting semi-structured interviews with senior staff and seeking documentary evidence of changes to organisational practice. Note also the inclusion of in-depth case studies within the research programme described in output indicator 1.4.1. Not all users will find tools/ services led to increased effectiveness due to factors unrelated to quality of Bond service (e.g. staff turnover, changes in financial situation); however Bond can increase rate of effectiveness through continuous improvement of tools/ services and of targeting. The Health Check, Evidence Principles and Effectiveness Toolkit are assumed to be the services most likely to increase organisational effectiveness for outcome 1.3. Predicted rates of effectiveness in output 1.3 are higher than for output 1.1 given additional steps between increased personal knowledge/ skills and increased organisational effectiveness (e.g. turnover, changes in responsibility); rates are less subject to change by Bond as the cohort of trainees differ from year to year. Reported effectiveness improvements from transparency (publishing to IATI) will be limited until more uses/ applications for data are developed and feedback mechanisms are strengthened; rate of improvements will increase with introduction of Transparency Survey and Information Platform. We also assume that others will generate more uses for data (e.g. DFID Aid Transparency Impact Fund)
|  | Achieved |  | 519 (54% of 961 trainees) | 659 (60% of 1,099) | 724 (67% of 1,138) | 1902
Source
Bond Annual Survey
| Outcome Indicator 1.2 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| # of UK organisations who received support from Bond or NIDOS citing evidence of an increase in their transparency as a result of improving their transparency [subset of group covered in outputs 1.2.1 and 1.2.3] | Planned | N/A | 15 | 30 (cumulative target) | 80 (cumulative target) | 80 (cumulative target by end of the grant)
|  | Achieved |  | 22 (22% of 102 orgs with IATI support) | 48% of users of our IATI support and 38% of users of the Transparency Review reported “some” or “systematic” organisational change as a result of that support in our February 2015 Outcomes Survey. | 111 (56% of users of IATI support, and 67% of users of Transparency Review) | 111
Source
Bond Annual Survey. Note where the same organisation used multiple services in different years, we have applied the "% reporting organisational change" score for the highest-scoring service that organisation used.
| Outcome Indicator 1.3 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| # of Bond or NIDOS members citing evidence of an increase in their effectiveness as a result of using one of more of the Bond or NIDOS effectiveness tools or services [subset of those in Output 1.4.2, i.e. Health Check, Evidence Principles and cost benchmarking study] | Planned | N/A | 60 (60% of 100 users) | 81 (60 from Year 1, plus 70% of 30 new users) | 97 (81 from Years 1 and 2, plus 80% of 20 new users) | 97 organisations (cumulative target)
|  | Achieved |  | 67 (62% of 109 users) | 81 (67 from Year 1, plus (32% of 43 new users = 14 in year 2) | 110 (81 from Y1 and Y2; plus 44% of 66 new users in Year 3) | 110
Source
Bond Annual Survey
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016) | Assumptions
Target audience* engages with and influences EU development policy and the post-2015 agenda | Target audience* plays a role in ensuring the EU's development policy and practice remains focused on poverty reduction | Planned | In 2013 no collective UK NGO contribution to formal consultations and policy dialogue on EU development policy. | At least one policy maker gives positive feedback showing the effects of London/Brussels-based event on their position (annual target) | At least one policy maker gives positive feedback showing the effects of London/Brussels-based event on their position (annual target) Development-focused dialogue with newly elected UK Members of European Parliament (MEPs). | At least one policy maker gives positive feedback showing the effects of London/Brussels-based event on their position (annual target) On-going dialogue with UK MEPs on EU development policy and practice. | Evidence that EU development policies reflect joint UK NGO / Concord positions, with a focus on poverty reduction remaining. (April 2016) | There is a continued desire from UK NGOs to prioritise influencing EU decision makers and continue to contribute to official policy consultations on European development policy and practice. The European Commission (and other relevant Directorates-General (DGs)) continue to seek input and submissions from civil society on European development policy and practice. It is a known challenge to get feedback from policy makers that NGO activity has had an effect on their position. Therefore, indication from one policy maker per year is a sufficient target, but does not imply that only one policy maker is impacted upon each year. This evidence will come from a different policy maker for each year of the project. There are rarely more than 2 official opportunities (i.e. European Commission (EC) consultations) per year so one piece of feedback is significant in this context. The policy makers targeted through this piece of work will depend on in-depth power analysis of active players, but will likely include MEPs, European Commission officials, ministers and officials from other Member States. The policy maker feedback will come from significant players in the relevant policy processes.
|  | Achieved |  | An external review of Bond's EU policy work included positive comments from 2 policy makers about the impact of Bond's work at policy level | SoS reply to Bond Foreign Affairs Council letter (9 Dec 2014 – ahead of FAC): “I continue to value your critical work with civil society networks in Brussels and other Member States to help achieve our shared objectives” Officials gave positive informal feedback at 19 January roundtable on EU aid – joint planning on how to achieve Bond asks from report. Ongoing dialogue with UK candidates / MEPs before and after the election, esp. with DEVE chair and UK MEP Linda McAvan
Source
Records of meetings and events, emails, records of phone conversations with policy targets; Comparison/analysis of our goals with key policy statements (Commission communications, Council conclusions and European Parliament reports)
| Outcome Indicator 2.2 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016) | Assumptions
| Target audience* plays a role in ensuring that the EU (and member states) deliver their aid commitments | Planned | Very limited progress on delivery of Busan aid effectiveness commitments. Limited political focus on aid effectiveness. No implementation plans of any Member State or the European Commission. NB: Bond to review annual milestones with DFID at the beginning of each year to identify any more specific indicators to evidence progress towards the target, given the specific EU policy landscape prevailing at that point. Limited action taken by Bond members towards this, but has been ad hoc. | Bond members contribute to NGO monitoring to the production of an annual report (Nov/Dec 2013) that tracks delivery of the commitment by the EU and Member States on aid effectiveness, including an annual launch event (location TBC) that presents the results to key decision-makers and opinion-formers. | Bond members contribute to the production of an annual report (Nov/Dec 2014) that tracks delivery of the commitment by the EU and Member States on aid effectiveness, including an annual launch event (location TBC) that presents the results to key decision-makers and opinion-formers. | Bond members contribute to the production of an annual report (Nov/Dec 2015) that tracks delivery of the commitment by the EU and Member States on aid effectiveness, including an annual launch event (location TBC) that presents the results to key decision-makers and opinion-formers. | Evidence of progress by European Commission to deliver their aid effectiveness commitments. At least four EU Member States publish Busan implementation plans and have commenced delivery of aid effectiveness commitments. (cumulative target) | Economic crisis - globally and in Europe - does not deepen further and destroy political will on aid effectiveness. The global partnership for effective development cooperation continues to function and operate at a senior political level. Continued desire from UK NGOs and European partners and CONCORD to continue focus and work programme on EU aid quality to 2015 and beyond. Bond members will be contributing to this process but the number and manner of this contribution depends largely on future policy developments. Examples of the contributions we might expect include commenting on Terms of References (ToRs) of NGO monitoring report, approving choice of consultant, commenting, quality checking drafts, attending EU meetings and participating in the process of organising a UK launch of the report.
|  | Achieved |  | The European Policy Group, with over 100 members, input into the annual AidWatch report, which was launched in Brussels in October 2013. | The European Policy Group, with 170 members, input into the annual AidWatch report 2014, which was launched in Paris and London, and produced a report on EU aid/the EU budget.
Source
Baseline: 2012 special AidWatch report on EU development effectiveness, official Busan implementation and monitoring framework.
| Outcome Indicator 2.3 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016) | Assumptions
| Target audience* has an effective voice in post-2015 dialogue | Planned | Present strength / level of activity and interactions of Beyond 2015 European Taskforce and Beyond 2015 international campaign (and Bond’s contribution to this) and Bond Beyond 2015 UK Group. | At least 4 joint activities supported, led, facilitated towards, at and in follow up to the UN General Assembly (GA) MDG Review Summit and intergovernmental processes including 2 global/regional influencing activities and 2 common positions and structured dialogues at UK level. (annual target) | At least 8 joint activities supported, led, facilitated around UN / intergovernmental process(es), EU processes and related civil society global and regional coordination including 2 global/regional influencing activities and 2 common positions and structured dialogues at UK level. (annual target) | At least 8 joint activities supported, led, facilitated towards, at and in follow up to the UN GA Post MDGs summit and new framework including 2 global/regional influencing activities and 2 common positions and structured dialogues at UK level. (annual target) | NGOs are convened/supported to participate in/contribute to the development of a post-2015 framework through at least 20 joint activities towards, at and in follow up to UN summits/ intergovernmental and international/regional process(es). Evidence that EU positions reflect joint UK NGO / Concord / Beyond 2015 European positions; the framework reflects Beyond 2015 international positions and Bond’s role and contribution is/has been valued internationally. (April 2016) | UK NGOs continue to prioritise post-2015 work including through Bond as a ‘national hub’ of Beyond 2015. UK government continues to value the role of Bond with UK NGOs in the UK on the post-2015 agenda. UK, European and international processes continue to value input from NGOs International negotiation processes to agree new framework stays on track Of the 4 joint activities each year, 1 will be at international level, 1 at EU level and 2 at UK level. We deem this to be the number of activities that will be required to maintain the voice of civil society in the post-2015 process. While the year one targets were exceeded by a big margin in the first year of the grant (reporting 21 activities against a target of 1), the environment during the next steps of the process will not be as open to civil society and the number of opportunities to engage would not reach the same level. The year 3 target will be reviewed at the end of year 2.
|  | Achieved |  | Bond led 27 joint activities with its target audience to influence the post-2015 dialogue (5 at EU level, 16 at UK and 6 at a global level). | Bond led 30 joint activities with its target audience to influence the post-2015 dialogue (28 focusing on EU processes and 2 at an international level).
Source
Self-assessment; survey(s) of Bond members, partners and other stakeholders; other sources depending on the nature of the activities, likely to include meeting minutes, reports and attendance lists from high level events or other workshops, and dissemination records of any reports or briefings.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.1 | Output Indicator 1.1.1 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016) | Assumption
Bond supports its target audience* in gaining the skills, knowledge and tools that enable them to make improvements in their practice. | # of individual participants in Bond’s training services (including open training and in-house training). (Milestones are for trainees each year and are not cumulative.) | Planned | 916 | 1000 (annual target) | 1100 (annual target) | 1210 (annual target) | 3310 (cumulative target) | Bond maintains a competitive and relevant Open- and In-House Training offer. Participants in Bond Conference sessions relating to Effectiveness and Learning are included in the figures for Output 1.1.3. Individual participation in training, networking and events is voluntary and thus quality content should result in high levels of increase in knowledge and confidence. Such increases, however, are expected to be lower for networking and events as these are free, compared to paid-for training, and as some groups are newly-established and will take time to agree areas of focus and common interest. We will seek to verify individual claims of benefits derived from Bond's training and networking opportunities by undertaking interviews with a sample of senior managers in NGOs and by examining documentary evidence. Output 1.1.4 is a new indicator, for which there is no pre-grant baseline. The milestone data for 2014 will serve as a baseline.
|  | Achieved |  | 961 | 1099 | 1138 | 3198
Source
Bond training records
| Output Indicator 1.1.2 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| Of those participating in training, # and % reporting an increase in personal knowledge and confidence as a result | Planned | 90% | 93% (annual target) | 95% (annual target) | 97% (annual target) | 97% (target for last year of grant)
|  | Achieved |  | 99% | 99% | 98.5% | 98.5%
Source
Annual survey
| Output Indicator 1.1.3 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| # of individual active participants in Bond’s networking services and events (specifically Funding, Transparency and Monitoring, Evaluation and Learning and Small NGO Working Groups, and related events and Bond Conference sessions). (Milestones are for participants each year, i.e. not cumulative.) | Planned | c.150 | 300 (annual target) | 440 (annual target) | 500 (annual target) | 500 (target for active participation by end of grant)
|  | Achieved |  | data not available (new indicator) | 930 (including 151 in the Ebola Response Hub; 791 in other) | 765 | 765
Source
Attendance records
| Output Indicator 1.1.4 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| Of those participating in networking and events, # and % reporting an increase in personal knowledge and confidence as a result | Planned | N/A | 75% (annual target) | 80% (annual target) | 85% (annual target) | 85% (target for last year of grant)
|  | Achieved |  | data not available (new indicator) | 93% | 92% | 92%
IMPACT WEIGHTING (%) |  | Source | [5 empty] | RISK RATING
10% |  | Bond post-training surveys; annual survey | [5 empty] | Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.2 | Output Indicator 1.2.1 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016) | Assumptions
Bond and NIDOS support their target audiences to become more transparent in the publication of information on their activities and results | # of UK-based organisations publishing data to the IATI standard to at least DFID minimum requirements, supported by Bond/ NIDOS | Planned | 101 | 125 (cumulative target: 101 plus 24 new orgs) | 145 (cumulative target: 125 + 20 new orgs) | 170 (cumulative target: 145 + 25 new orgs) | 170 (cumulative target) | It is our assumption that the main driver of publishing to IATI among UK organisations will be DFID contractual requirements. We assume that for organisations to voluntarily publish to IATI or go beyond the DFID minimum, they will need to (a) see published data being utilised in practical and accessible ways for improving accountability or other purposes; and (b) find the process of becoming more transparent relatively low-cost and low-risk. We also assume that becoming more transparent through other means (e.g. publishing information on organisations' own websites) can generate information that will increase accountability. The target audience here is UK-based organisations. Bond/ NIDOS members and DFID grant holders who are not Bond members will be supported with funding from this grant. Commercial organisations and other donors may be supported by Bond on a cost-recovery basis. It is assumed that we will capture examples of good practice through the Transparency Survey and Transparency Working Group and share this with the sector to provide peer encouragement; it is assumed that Bond can show the utility and value of increased transparency to organisations, linking it to broader issues of accountability, including to beneficiaries. Bond will undertake research to capture examples of good practice whether from UK NGOs, NGOs in other countries or other actors within the aid chain. The target audience for output indicator 1.2.2 is the combined Bond, NIDOS and CADA membership. Targets for usage of tools and subsequent increases in effectiveness have been agreed with NIDOS, and are pending with CADA. The effectiveness resources include Bond’s tools and the NIDOS Effectiveness Toolkit.
|  | Achieved |  | 132 | 170 UK-based organisations (plus 34 non-UK) | 185 UK-based organisations (plus 58 non-UK) | 185
Source
IATI Registry data plus Bond/ NIDOS records of transparency support provided (training, 1:1 support)
| Output Indicator 1.2.2 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| # and % of UK-based organisations publishing data to the IATI Standard that are going beyond the DFID minimum requirements (i.e. publishing to more than just the basic fields and/ or more than their DFID funding) | Planned | No data available (cannot be recreated from IATI records) | DFID and IATI Secretariat supported by Bond to revise NGO minimum requirements; 5% (6 orgs) go beyond minimum [MAY REVISE ONCE DevInit PROVIDE CURRENT DATA] | 15% (22) go beyond minimum (cumulative target) | 25% (42 orgs) go beyond minimum (cumulative target) | 25% (42 orgs) go beyond minimum (target for last year of grant)
|  | Achieved |  | Support provided; min. requirements not defined/ communicated by DFID. | 19% (32) publishing information above and beyond just DFID funding (81 publishing to more fields on DFID funding) | 30% (59 orgs) publishing info above DFID minimum (comprising 26 publishing more than just DFID grants; 10 publishing more than just DFID grants and more fields than required; and 23 publishing only on DFID grants but more fields than required). Note that the denominator here is 200 UK-based orgs publishing to IATI, of whom 185 have received Bond support. | 30% (59 organisations)
Source
IATI Registry data, checked using Data Validator tool
| Output Indicator 1.2.3 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| # of Bond and NIDOS members participating in an annual Transparency Review, measuring the coverage of NGO data on activities and results published to IATI and/ or through their own websites [was: O/c I 1] | Planned |  | Consultations held and tool developed for Transparency Survey | 30 orgs in first survey; 50 orgs signed up to the second survey | 50 orgs in second completed survey; viability of sustaining the Transparency Review investigated | 80 organisations in total over the project period
|  | Achieved |  | Consultations held and tool developed. | 49 organisations in first cohort; 26 currently signed up to Cohort 2 (registration opened in late Feb 2015) | 49 organisations in cohort 2 (includes 5 repeat users who were also in cohort 1; so 44 new users) Insufficient willingness to pay from orgs to make the Review a paid-for service; active efforts underway to seek grant funding for Cohort 3. | 93 [49 in each of Cohort 1 and Cohort 2, with 5 repeat users in cohort 2)
Source
Bond Transparency Assessment
| Output Indicator 1.2.4 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| # of supporting resources developed by Bond to help organisations improve scores in the Transparency Review | Planned | n/a | n/a | 1 resource developed | 2 resources developed (cumulative target) | 2 resources developed
|  | Achieved |  | n/a | 1 (guidance on developing Open Information Policies) | 2nd resource = research on publishing results ("Making Evaluations Work Harder in International Development") | 2 resources developed
Source
Bond Transparency Assessment
| Output Indicator 1.2.5 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| # of UK-based INGOs demonstrating use of IATI data to support their effectiveness and transparency | Planned | No current use of IATI data by UK-based INGOs. | Research and scoping for potential uses of IATI data to support NGO effectiveness and transparency underway | 22 (cumulative target) | 42 (cumulative target) | 42 organisations are using IATI data to increase their effectiveness and transparency
|  | Achieved |  | Scoping commenced. | 25 | 43 (40% of 73 UK-based orgs supported in Year 3; plus 20% of 70 UK-based orgs supported in Year 2 but not also in Year 3) | 43
Source
Bond Reporting and Survey of Members, plus generation of case study examples profiling organisations making use of IATI data
| Output Indicator 1.2.6 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (date)
| Bond’s transparency support and influencing contributes to increased transparency by organisations that are not members of Bond/ NIDOS [qualitative milestones re IATI Civil Society Organisation Working Group (CSO WG), CSO guidance work with Development Initiatives (DI), commercial suppliers, open philanthropy, other Platforms...] | Planned |  | Bond with Development Initiatives finalise CSO Guidance on Publishing to IATI | Bond supports 2 other national NGO platforms with guidance on IATI and Transparency; publishes 1 piece of research on improving transparency (cumulative target) | Bond supports 4 other national platforms with guidance on IATI and transparency, and publishes 2 publications on improving transparency (cumulative target) | Bond supports 4 other national platforms with guidance on IATI and transparency, and publishes 2 publications on improving transparency
|  | Achieved |  | Guidance finalised and on IATI website. | Partos (Netherlands) and Interaction (USA) supported with peer learning on IATI. Cohort 1 report on Transparency Review published. | 2 x Belgian platforms supported. Cohort 2 report of Transparency Review published. Discussion paper on "IATI and Publishing Results" published | 4 platforms (USA, Netherlands, 2 x Belgian) supported; 3 publications produced
IMPACT WEIGHTING (%) |  | Source | [5 empty] | RISK RATING
15% |  | IATI Registry Data; feedback from those supported by Bond | [5 empty] | Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.3 | Output Indicator 1.3.1 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (date) | Assumption
Bond develops and provides new effectiveness tools and services that are responsive to evolving needs of members, within a sustainable business model | # of new tools/ resources/ services to improve effectiveness developed by Bond in response to evolving needs of target audience (e.g. on Value for Money (VfM), beneficiary feedback, evidence-sharing, organisational governance, Futures ) that Bond members describe as useful | Planned | N/A | 5 [Governance; Monitoring, Evaluation & Learning (MEL); Transparency working group; HealthCheck upgrades; IATI CSO Guidance) | 15 (cumulative target: 5 from year 1 plus 10 new) | 20 (cumulative target: 15 from years 1 and 2, plus 5 new) | 20 new tools/ resources/ services over the grant lifetime | This assumes that new tools/ resources/ services will be built around key emerging issues in effectiveness and as follow-on resources to the Health Check (moving from diagnosis to action). The pace of new tool/ resource/ service development will be greatest in Year 2 as we build on learning from Year 1, and we consolidate in Year 3. Assumes Members remain willing to share information on their effectiveness needs openly with Bond. Assumes Bond engages in continual learning and undertakes market analysis to ensure we provide relevant and competitive tools/ resources/ services.
|  | Achieved |  | 5 (Monitoring, Evaluation and Learning Working Group (WG), Transparency WG, Commercial Contracts WG; IATI CSO Guidance; Investing in MEL study.) | 17 (12 new in Year 2, added to 5 in Year 1) | 22 (5 new in Year 3: Impact Evaluation Commissioners' Guide; Health Check Influencing Resources; Cost Benchmarking Survey and Report; Health Check Big Picture Report; Evaluation Terms of Reference Top Tips) | 22
Source
Bond monitoring records of service take-up
| Output Indicator 1.3.2 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (date)
| A robust business model is in place for UK effectiveness services to ensure they are financially sustainable and strategically placed to further effectiveness and transparency within international development |  | N/A | Analysis of support needs of target audience complete; initial package of services available and income targets confirmed for Years 2 and 3 | Net annual income target for effectiveness services of £30k met | Net annual income target for Effectiveness target of £120k met | Net annual income target for Effectiveness target of £120k met
|  | Achieved |  | Training review completed; Outcomes Survey (to inform needs) delayed. Income targets set. | £34k | Initial estimate: £80000 | Target not met (£80k)
Source
Bond
| Output Indicator 1.3.3 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (date)
| Bond facilitates consultation and engagement by members with the DFID Civil Society & Partnership Review |  | N/A | N/A | N/A | 5 twitterchats 2 face-to-face meetings 1 consolidated submission facilitated by Bond | 5 twitterchats 2 face-to-face meetings 1 consolidated submission facilitated by Bond
|  | Achieved |  |  |  | 5 twitterchats; 2 face-to-face meetings; 1 consolidated submission facilitated by Bond | 5 twitterchats; 2 face-to-face meetings; 1 consolidated submission facilitated by Bond
IMPACT WEIGHTING (%) |  | Source | [5 empty] | RISK RATING
10% |  | Bond records and social media reports | [5 empty] | Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.4 | Output Indicator 1.4.1 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016) | Assumption
Bond develops and shares improved knowledge for the sector on how organisational effectiveness is affected by the provision and uptake of effectiveness tools and services | Bond conducts a research programme incorporating at least 8 NGO case studies and 3 overview reports tracking how the use of Bond’s and NIDOS’ different effectiveness tools and services influences learning and changes in practice over time in different types of NGOs, including consideration of impact on the final beneficiary (aligned with DFID and members’ strategic priorities) | Planned | N/A | At least six two-year case studies recruited as a sample of UK NGOs and programme/sector types; TORs agreed between DFID, Bond and case study organisations, incorporating Southern partner perspectives. | Interim report produced highlighting process for service uptake and initial outcome journey. Up to 3 additional short-term case studies undertaken. Learning activities and feedback loops ensure this is fed back into effectiveness resource development. | Data on outcomes of service usage continues to be generated to produce key learning about the impact of the effectiveness tools/ services on practice, so also helping to further improve the tools and their use; final report produced. | Data on outcomes of service usage continues to be generated to produce key learning about the impact of the effectiveness tools/ services on practice, so also helping to further improve the tools and their use; final report produced. | At least six organisations are willing to be case studies and it is possible within the timescale to provide some indication of impact on organisational effectiveness; impacts on the final beneficiary are assumed not to be measurable by Bond. Bond commissions a high-quality research study using a robust methodology agreed and overseen by a steering group which will include DfID and an academic adviser. Interim feedback, where relevant will be used for learning and course correction throughout the grant period. The milestones for the usage of tools/ services are cumulative and based on at least one tool/ service being used; some NGOs will use more than one tool. Bond and NIDOS each have internal targets for use of each of the tools within the programme. The targets for usefulness assume Bond will make continuous improvements based on user feedback. Assumptions about steady growth in targets around usage of Bond's effectiveness resources are based on a number of factors: - Bond's and NIDOS's growing membership - Communication and promotion of the tools - Increasing alignment between Bond's effectiveness work and our training and support offer - Increased insight into needs and marketing strategies targeting small NGOs By 'useful', we mean that those using Bond and NIDOS effectiveness tools and services find them of practical value in improving organisational performance.
|  | Achieved |  | Terms of reference and criteria for cast studies drafted and agreed with DFID. Revised MEL framework developed incorporating stronger outcomes data. | Interim report covering 8 case studies produced (6 Bond members and 2 NIDOS members). 0 short-term case studies undertaken. 2 x Outcomes Surveys carried out. | Final case study overview report produced; 8 detailed case studies and 2 mini-case studies finalised. 3rd Outcomes Survey completed. Final external grant evaluation underway. | Annual data on outcomes of service usage generated and used for continuous improvement, along with in-depth case study research.
Source
Bond Effectiveness Research programme
| Output Indicator 1.4.2 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| Number of Bond and NIDOS members using 1 or more of the Bond or NIDOS effectiveness tools or services, disaggregated by organisational size. | Planned | N/A (data not collected previously on all services) | 170 (of whom 35 are "small") | 200 (of whom 50 are small; cumulative target: 170 plus 30 new users) | 250 (of whom 75 are small; cumulative target; 200 plus 50 new users) | 250 (of whom 75 are small; cumulative target)
|  | Achieved |  | 163 as of 31/12 (of whom 32 are small) [or 109, of whom 17 small, excl training; target originally was 105] | 251 Bond and NIDOS members (of whom 53 Bond members are small) | 293 (of whom 114 small) | 293 (of whom 114 small)
Source
Usage/sign up numbers for: Bond Health Check, Bond Impact Builder, NIDOS Organisational Effectiveness Toolkit and Evidence Principles/ Checklist; Transparency support; MEL/ Transparency/ Funding Working Group members attending at least 1 meeting or participating in MyBond fora; and organisations sending participants to Bond training. Usage of additional tools/ services under output 1.3.1 will also be included. Data will be disaggregated by Bond membership classification, where "small" means expenditure of >£500,000 per year.
| Output Indicator 1.4.3 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| Of those using tools or services each year, % reporting that they found the tools or services useful (i.e. score 7 or more out of 10 in feedback surveys) | Planned | N/A | 75% of users | 85% of recorded Year 2 users; (annual target) | 90% of recorded Year 3 users (annual target) | 90% of recorded users in final year
|  | Achieved |  | 79% | 196 (78% of users) | 84% of users | 84% of users
Source
Annual or rolling Outcomes Survey; weighted average of respondents for all tools and services scoring 7 or above on "usefulness of service" . Verified through case studies within research programme and by sample of additional interviews
| Output Indicator 1.4.4 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| Number of other organisations or platforms using or recommending usage of 1 or more of the Bond or NIDOS effectiveness tools or services | Planned | N/A | 90 | 100 (cumulative) | 110 (cumulative) | 110 (cumulative)
|  | Achieved |  | 71 [or 20 excl training] | 134 | 136 (cumulative) [note that 17 orgs previously counted as non-members have since joined Bond and been moved from this indicator to 1.4.2] | 136 (cumulative)
IMPACT WEIGHTING (%) |  | Source | [5 empty] | RISK RATING
15% |  | Usage/sign up numbers for: Bond Health Check, Bond Impact Builder, NIDOS Organisational Effectiveness Toolkit and Evidence Principles/ Checklist; Transparency support; MEL/ Transparency/ Funding Working Group members attending at least 1 meeting or participating in MyBond fora; and organisations sending participants to Bond training. Usage of additional tools/ services under output 1.3.1 will also be included. | [5 empty] | Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2.1 | Output Indicator 2.1.1 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016) | Assumptions
Bond supports its target audience* to effectively engage with and influence European development policy and practice | Collective UK and pan-European NGO action(s) to support Member States to move towards the 0.7% aid target and ensure the new MFF includes adequate finance and instruments for aid and development. | Planned | Annual AidWatch project having relatively limited political impact. Civil society successful in pushing for aid to remain on the political agenda (Foreign Affairs Council [FAC], European Council meeting, etc). No civil society monitoring, tracking and action on the EU development budget ahead of MFF being agreed. | NGOs publish annual reports and deliver influencing activities that track and push the EU and Member States to deliver their aid quantity and quality commitments. | NGOs publish annual reports and deliver influencing activities that track and push the EU and Member States to delivery their aid quantity and quality commitments. Annual AidWatch report, London and Brussels launch events, capital-level actions. NGO responses to May 2014 and November Foreign Affairs Council (FAC) 2014 (letters, briefings, meetings with EU officials etc.) 1st annual MFF tracker (report) published. | NGOs publish annual reports and deliver influencing activities that track and push the EU and Member States to delivery their aid quantity and quality commitments. Annual AidWatch report, London and Brussels launch events, capital-level actions. NGO responses to May 2015 and November FAC 2015 (letters, briefings, meeting with EU officials etc.) Briefing papers on any new financing for development commitments made by EU Member States following 2015 0.7% target. | Evidence of progress by European Commission to deliver their aid effectiveness commitments (including implementation plans), aid remains on the EU's political agenda each year and evidence that EU development policy remains focused on poverty reduction. AidWatch project and other actions have increased political impact – halt the reverse in downward aid trends, official response to report/actions from European Commission and Member State governments, aid remains on the political agenda each year, effective civil society action on the EU development budget within the new MFF. (April 2016) | Economic crisis - globally and in Europe - does not deepen further and destroy political will on aid and development. Continued desire from UK NGO to maintain a focus on EU aid levels to 2015 and beyond and prioritise influencing EU decision makers. The global partnership for effective development cooperation continues to function and operate and a senior political level. Definition of submission: a written document, either in response to a formal Commission consultation or the dissemination of Bond research, policy paper or briefing paper to key stakeholders. Definition of engagement: Bond and/or its members attend a policy dialogue with key external stakeholders, key external stakeholders attend/speak at the Bond event or activity, or they provide feedback on a Bond submission. There will be at least two opportunities each year to contribute to consultations, reviews, enquires and dialogues, be they formal or informal. The new International Development Commissioner will be open to engagement with European civil society There will at least be a small cohort of newly elected UK MEPs that are interested in international development issues There will be at least one UK MEP on the European Parliament’s International Development committee By "limited" political impact of the Annual AidWatch, we mean that there is greater potential to have impact on decision makers than has been realised to date. Adequate financing is Europe's contribution to the total global financing needed to achieve the MDGs, including member states meeting their collective 0.7% commitment by 2015. These milestones are annual rather than cumulative.
|  | Achieved |  | AidWatch’s report published and a number of influencing activities were delivered in the UK and in Europe. | AidWatch report produced, with 2 launch events, 3 other major activities (media and events). 4 submissions and ongoing influencing: briefings, meetings, debriefings around the May and Dec FAC and informal FAC in June 14 and March 15. Report with an analysis and recommendations on the MFF and Agenda for Change published. | Bond initiated a Europe-wide action to push for an EU recommitment to aid ahead of the EU Foreign Affairs Council – this included a joint twitter day of action, joint media work and influencing work with joint messages (letters and meetings); Bond contributed to 1 publication and influencing work around the EU’s aid commitment and recommended action ahead of the FAC and FFD3 conference: “What’s in the commitment? Unlocking 0.7%” (CONCORD, May 2015) Bond is leading the development of the Terms of Reference for the EU Aidwatch report Bond produced a paper with UKAN on ‘priorities for ICAI’ upon the appointment of the new Commissioner – with very positive feedback from ICAI on how helpful this was, again with UKAN we convened a roundtable with ICAI to hear their planned priorities and share sector perspective – again with very positive feedback On EU aid we continue to do ongoing work within CONCORD AidWatch on an EU aid accountability report; paper on refugee costs; engagement around UN DCF. Bond-supported and facilitated policy and advocacy activities towards Financing for Development conference in Addis Ababa influence UK and EU commitments for an ambitious, adequate and balanced financing framework.
Source
Baseline: DFID assessment; 2012 FAC conclusions, EU Member States’ commitments, 2012 AidWatch project including the 2012 AidWatch report.
| Output Indicator 2.1.2 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| Collective UK and pan-European NGO action(s) to ensure that aid effectiveness remains a core focus of the EU’s approach to aid and development | Planned | Very limited collective action; following the Busan High Level Forum, there has been a decrease in NGO focus and action on the aid effectiveness agenda | At least 2 events and activities that convene key EU policy makers and NGOs (annual target) | At least 2 events and activities that convene key EU policy makers and NGOs (annual target) | At least 2 events and activities that convene key EU policy makers and NGOs (annual target) | At least 6 events and activities throughout the project that convene key EU policy makers and NGOs (cumulative target)
|  | Achieved |  | Bond has delivered a number of activities that convened EU policy makers and NGOs. | 3 events and activities were convened around 3 moments to engage EU policymakers and NGOs | Contributions to “CSO Partnership for Development Effectiveness” (CPDE) position paper, side event and influencing work ahead of and at FFD3, which included influencing the EU; Continuous influencing on the EU’s role on development effectiveness and aid quantity as part of FFD engagement (see below – 3 submissions and 9 formal meetings) Bond has engaged in ongoing dialogue with MEPs, contributing to an MEP roundtable on FFD with Concord and a roundtable with the EU parliamentary delegation at FFD who were receptive and advocated many civil society positions Around FFD we influenced the UK government, EU, UN and other stakeholders on an ambitious and balanced FFD 3 outcome with a send-off briefing, joint and individual lobbying meetings with FFD leads at DFID and EU delegations; contributions to a global CSO response and global CSO declaration. Ahead of the summit we’ve placed two articles in the media and an open letter (blog), conducted one public stunt; produced 3 different blogs; and an activities evaluation for our members.
Source
Records of events and activities, feedback from NGO participants and policy makers, progress made by donors against the official Busan monitoring framework, official statement from member states, agenda and outcomes of official meetings and council conclusions.
IMPACT WEIGHTING (%) | Output Indicator 2.1.3 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
25% | Bond's target audience* contributes to European Commission consultations and strategic key moments on European policy and practice | Planned | In 2012 no collective UK NGO contribution to formal consultations and policy dialogue on EU development policy. | At least 2 submissions per EU policy consultation on EU development policy and practice. (annual target) | At least two collective UK NGO contributions to reviews or discussions of policy submitted by Bond. These might include submissions to policy consultations, reviews, enquires, dialogues, and engagement with the new Commission and International Development Commissioner and newly elected UK MEPs (especially those on the European Parliament’s International Development Committee). (annual target) | At least two collective UK NGO contributions to reviews or discussions of policy submitted by Bond. These might include submissions to policy consultations, reviews, enquires, dialogues, and engagement with the new Commission and International and International Development Commissioner and key UK MEPs. (annual target) | UK NGOs are convened and supported to actively and effectively participate in and contribute to the development of European development policy and practice. (April 2016)
|  | Achieved |  | No opportunities for submissions, but other relevant work has taken place. | 6 submissions and major activities ahead of and post the EP elections 9 submissions and activities related to the modernisation of ODA and the Development Assistance Committee High Level Meeting 11 submissions and activities related to Financing for Development negotiations | 1 contribution from Bond’s European Policy Group to the EC’s consultation on the EU Gender Action Plan (April 2015). 3 submissions on FFD process shared with UK, EU, and G77 policy makers; 1 meeting with the new EU presidency (Luxembourg) on priorities for Presidency including aid, FFD, SDGs; Influencing key EU policy makers around FFD3, aid effectiveness and quantity, including meeting the European Commission, FFD MEP delegation, and EU member states delegations, Brussels, during the drafting session in NY and at the FFD3 conference in Addis (9 convened meetings, about 20 meetings in the hallway); Engaging with MEPs as part of Bond’s convening role on the EYD, with one Q&A sessions organised with the EP’s DEVE chair in London, and engaging around key messages with 10 UK MEPs. The EPG has developed a advocacy strategy to focus on gender as well as delivering a Roundtable with representation from Brussels and Luxembourg
|  | Source | [5 empty] | RISK RATING
|  | Submission by UK NGOs to European policy consultations. | [5 empty] | Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2.2 | Output Indicator 2.2.1 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016) | Assumptions
Bond supports its target audience* to effectively engage with and influence the process and outcome of the post-2015 agenda (at both European and international level) | Number of supported efforts (submissions, dialogues etc.) at the national and Brussels/pan EU level influencing both the European Institutions and Member States to agree official EU position on post-2015. | Planned | Present strength / level of activity and interactions of Beyond 2015 European Taskforce (and Bond’s contribution to this). | At least 1 joint influencing activity supported, led, facilitated towards, at and in follow up to EU processes and related civil society regional coordination. | At least 7 joint influencing activities supported, led, facilitated towards, at and in follow up to EU processes and related civil society regional coordination. (annual target) | At least 5 joint influencing activities supported, led, facilitated towards, at and in follow up to EU processes and related civil society regional coordination. (annual target) | NGOs are convened and supported to participate in/contribute to the development of a post-2015 framework through at least 13 Bond-supported efforts in the EU. Evidence that EU positions reflect joint UK NGO / Concord / Beyond 2015 European positions; Bond’s role and contribution is/has been valued in the EU. (April 2016) | International civil society continues to value the contribution of UK NGOs including through Bond at the EU and international levels. A critical mass of UK NGOs prioritise international influencing in the post-2015 process with partners. The official UN process is legitimate and responsive to the voices of civil society (and of those directly affected by poverty and injustice) and trust is sufficiently high for engagement. The UN Special Event in September 2013 improves the prospects for a post-2015 framework, and launches a single, unified process where issues of sustainable development, poverty and injustice are fully integrated. Beyond 2015 has strong foundations for advocacy in the intergovernmental process, and is effective in influencing national, regional and international decision-making bodies. While the year one targets were exceeded by a big margin in the first year of the grant (reporting 21 activities against a target of 1), the environment during the next steps of the process will not be as open to civil society and the number of opportunities to engage would not reach the same level. The year 3 target will be reviewed at the end of year 2.
|  | Achieved |  | Bond has led 5 joint influencing activities at EU level and 16 at UK level. | Bond delivered 28 joint influencing activities, including more than 15 policy dialogues with the UK government and Bond published two major research reports focused on the SDG framework. | Bond has played an active role in the EU Post-2015 Taskforce, contributing to at least 4 position papers and responses to the zero draft and attending planning and coordination meetings in Brussels. Bond has engaged in Concord development of an 'EU Plan for Implementation' to influence the delivery of the post-2015 framework.
Source
Self assessment; survey(s) of Bond members, partners and other stakeholders; independent evaluation.
| Output Indicator 2.2.2 |  | Baseline | Milestone 1 (2014) | Milestone 2 (2015) | Milestone 3 (2016) | Target (2016)
| Number of supported efforts (submissions, dialogues etc.) at the national / regional / international levels aimed at influencing the UN and intergovernmental processes towards the Global Goals. | Planned | Present strength / level of activity and interactions of Beyond 2015 international campaign (and Bond’s contribution to this). | At least 1 joint influencing activity supported and led by Bond, towards, at and following the UN General Assembly (UNGA) MDG Review Summit and subsequent intergovernmental process set up after September 2013. | At least 1 joint influencing activity supported and led by Bond, towards, at and following intergovernmental process(es) and related civil society global coordination. (annual target) | At least 7 joint influencing activities supported and led by Bond, towards, at and following the UN GA Post MDGs summit (September 2015) and subsequent meetings on implementation of and indicators for the Global Goals (including the IAEG Meeting in October 2015). (annual target) | At least 9 joint influencing activities supported and led by Bond, towards, at and following relevant policy processes (cumulative target)
|  | Achieved |  | Bond has led 6 joint influencing activities at the global level | 2 joint influencing activities supporters at intergovernmental level: convening and coordinating UK NGOs in New York at the 2014 UN General Assembly (UNGA), and supporting the organisation of an international civil society conference convened by Beyond2015 in Copenhagen. | Bond convened UK civil society advocacy at the last Intergovernmental Negotiation towards UNGA, drafting joint responses to Zero Draft and other collective inputs Bond organised a series of policy dialogues with the DFID negotiations team ahead of and at the IGN sessions as well as at the Post 2015 Summit. Bond co-hosted the only official civil society side event at the Post 2015 Summit show-casing Members States with ambitious implementation plans. Bond organised an event with the SoS for International Development at the Post 2015 Summit on 'Financing the Goals'. Bond produced a series of research papers in 2015, on SDG indicators on inequality and climate change and the governance architecture in the UK. Bond convened a roundtable to discuss options for UK implementation, attended by 6 government department and select committee representatives. Bond chaired the global Beyond 2015 Indicators Task Force ahead of the Bangkok IAEG meeting on SDG indicators, supporting global civil society advocacy on the process. | At least 9 joint influencing activities supported and led by Bond, towards, at and following relevant policy processes (cumulative target)
IMPACT WEIGHTING (%) |  | Source
25% |  | Self assessment; survey(s) of Bond members, partners and other stakeholders; independent evaluation, records activities support relating to external events.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%) | RISK RATING
Minor
INPUTS (HR) | DFID (FTEs)
*The programme's overall target audience is UK NGOs including Bond members, UK development NGOs that are not Bond members and other strategic partners where relevant such as CONCORD. The Effectiveness Programmes primary target audience are Bond and NIDOS members, but targets for non-members include WIDH and CADA members in Wales and Northern Ireland respectively. The specific cohort of each area of work (as a sub-group of the overall target audience) will be specified in the annual report and baselines.

## Activities Log
OUTPUT 1 | ACTIVITY 1.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
| ACTIVITY 1.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| ACTIVITY 1.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
OUTPUT 2 | ACTIVITY 2.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
| ACTIVITY 2.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| ACTIVITY 2.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
OUTPUT 3 | ACTIVITY 3.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
| ACTIVITY 3.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| ACTIVITY 3.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
OUTPUT 4 | ACTIVITY 4.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
| ACTIVITY 4.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| ACTIVITY 4.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
OUTPUT 5 | ACTIVITY 5.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
| ACTIVITY 5.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| ACTIVITY 5.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
OUTPUT 6 | ACTIVITY 6.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
| ACTIVITY 6.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| ACTIVITY 6.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer